TAYO  /  GO-TO-MARKET PLAN

Go-to-Market Plan

How Setnayan wins the first 1,500 paying couples in 12 months — and starts the compounding loop.

Document version

v1.0 — May 2026

Date

May 2026

Status

Confidential — Internal Strategy

# 1. The Year One Question

How does a brand-new wedding app, with zero recognition, in a market dominated by free tools and a few well-known global generalists, get to 1,500 paying couples in twelve months — and seed the compounding guest-to-couple loop that makes Year 2 exponentially cheaper?

This document is the answer. It is not a marketing plan; it is a sequenced operating plan that names every channel, every partnership, every milestone, and every budget line that produces the Year 1 outcome.

Year 1 targets (per V1 spec, Section 14.1): 5,000 couple sign-ups, 1,500 paid conversions (30%), 1,200 active completed events, average 120+ guests per event, 70%+ guest QR activation rate, NPS 50+ couples / 40+ guests.

# 2. GTM Strategy On One Page

The Setnayan GTM strategy rests on five pillars. Each pillar maps to a chapter in this document.

| # | Pillar | What It Means | Year 1 Outcome |
| --- | --- | --- | --- |
| 1 | Vendor distribution | Setnayan doesn't acquire couples directly first — it acquires them through the suppliers couples already trust. | 30–40% of paid couples come from vendor referrals at near-zero CAC |
| 2 | Earned media + content | Bride and Breakfast PH, Rappler Lifestyle, Filipino wedding podcasts, TikTok influencer partnerships. | 5,000+ inbound waitlist signups, 30+ earned media placements |
| 3 | Paid acquisition (Meta + TikTok) | Targeted at newly-engaged PH women 25–35 in NCR, Cebu, Davao. | CPL ≤ ₱150; total paid acquisition spend ₱600K–₱1.2M Year 1 |
| 4 | Compounding guest loop | Every paid wedding generates ~100 guest accounts. Post-event marketing converts a fraction back to paying couples in months 12–24. | Year 2 cohort revenue ~₱19.5M from Year 1 guest base |
| 5 | Founder-led storytelling | Founders publish weekly product builds, customer stories, lessons learned. Treat the company as a media channel. | Trust premium that lets Setnayan charge while competitors are free |

# 3. The First 90 Days

The first 90 days set the launch trajectory. Six concrete deliverables, sequenced to compound on each other.

## Days 1–30: Foundation

- Sign 10 vendor partnership LOIs (3 caterers including Hizon's, 5 photographers, 2 venues in Tagaytay/Cebu).

- Recruit 10 concierge pilot couples via Bride and Breakfast PH and direct introductions; deliver Premium-tier value with manual backend.

- Launch Setnayan waitlist landing page; drive PHP 100K paid traffic to validate ≤₱150 CPL.

- Publish founder origin story on LinkedIn, Medium, Bride and Breakfast PH, and Rappler Lifestyle.

- Stand up customer support: in-app chat (Intercom or similar), email (hello@setnayan.com), 4-hour SLA business hours.

## Days 31–60: Distribution

- Onboard the first 50 vendor partners with co-listing program; train them on the QR identity story.

- Begin TikTok and Instagram content series with 3 nano-influencer brides documenting their Setnayan planning journey.

- Submit Setnayan for App Store and Play Store launch; secure App Store editorial pitch.

- Run Concierge Wedding Pilot: deliver 3 weddings using a partially manual backend, charge full Premium tier; measure NPS.

- Begin earned media outreach: 30 PH wedding journalists and bloggers receive briefing kit + early access.

## Days 61–90: Soft launch

- Soft-launch V1 to waitlist. First 500 couples get founding-member discount (₱500 off Premium).

- Activate paid Meta and TikTok campaigns at scale; weekly cohort review of CPL, conversion, and add-on attach rate.

- Feature 3 concierge pilot couples in case-study posts; pitch each story to lifestyle press.

- Sign V2 vendor marketplace LOIs with the top 25 PH wedding vendors; set Q1 2027 marketplace launch target.

- Publish first quarterly update — public-facing transparency (sign-ups, paid couples, NPS, biggest mistake).

# 4. Distribution Channel Strategy

Setnayan's CAC math only works if vendor distribution carries 30–40% of paid couple acquisition. The remaining 60–70% comes from earned media, paid social, and the post-event guest loop. Each channel is sequenced and budgeted below.

## 4.1 Vendor partnerships (zero-CAC)

Wedding suppliers — caterers, photographers, coordinators, venues — already have the trust of newly-engaged couples. Setnayan's wedge is to be the technology layer that supplements those vendors' service delivery, not a competitor to them. Sequence:

- Q1: Sign Hizon's Catering, top 10 PH photographers, 3 Tagaytay venues, 2 Cebu venues. Co-listing only — no commission in V1.

- Q2: Expand to 30 vendor partners; introduce Vendor Photo Licensing (V1.5) and Coordinator Partnership Program.

- Q3: 50 vendor partners; first measurable referral revenue; case studies with top 5 referring vendors.

- Q4: 100 vendor partners; V2 marketplace LOIs with top 50 brands; Q1 2027 marketplace launch.

## 4.2 Earned media

| Outlet / Channel | Year 1 Goal | Approach |
| --- | --- | --- |
| Bride and Breakfast PH | 3+ feature pieces, 1 sponsored series | Pitch the QR identity story; offer exclusive case studies |
| Rappler Lifestyle | 1–2 founder profile pieces | Lead with the privacy-first / DPA story angle |
| Inquirer Lifestyle / Manila Bulletin | 1 feature each | Lead with PH wedding industry data + Setnayan origin story |
| Filipino wedding podcasts | 5+ founder appearances | Direct outreach; offer co-branded podcast giveaways |
| TikTok / IG nano-influencer brides | 10–15 documented planning journeys | Comp Premium tier in exchange for content series |
| LinkedIn (founder-led) | Weekly product / lesson posts | Build founder brand; investors and operators read these |
| Medium / Substack | Quarterly long-form essays | Strategy framing for investors and partners |

## 4.3 Paid social acquisition

Meta and TikTok are the highest-ROI paid channels for newly-engaged PH women 25–35. Budget: ₱600K–₱1.2M across Year 1, weighted toward months 4–9.

| Channel | Audience | Creative Strategy | KPI |
| --- | --- | --- | --- |
| Meta (FB + IG) | PH women 25–35, recently engaged, NCR/Cebu/Davao | UGC-style 'a day in my Setnayan planning' video reels | CPL ≤ ₱150 |
| TikTok | Same audience, plus organic reach | Behind-the-scenes founder content, customer stories | CPM efficient, organic amplification |
| Google Search | High-intent keywords ('wedding planning app Philippines') | Conversion-focused landing pages; 3 versions A/B'd | ROAS ≥ 3x |
| Influencer-paid (5–10 mid-tier) | Niche PH lifestyle creators | Single-event sponsorship of one wedding each | Cost per lead ≤ ₱120 |

## 4.4 The compounding guest loop (Setnayan's secret weapon)

Every paid wedding generates ~100 guest accounts. Each guest account is a candidate future couple. Year 1's loop produces ~150,000 candidate accounts, with a target 2% conversion to paying couples within 24 months — ~3,000 future weddings, ~₱19.5M trailing revenue. Mechanics:

- Real-time soft banner: 'Loved this experience? Plan your own event with Setnayan. Tap for one-time discount.'

- Day 1 post-event: 'Your album is ready' notification with embedded soft CTA.

- Week 1 post-event: email — 'Re-live the moments. When you're ready, we're here.'

- 1-year anniversary: 'One year ago today: Maria & Juan's wedding. Browse your album.'

- Trigger-based: when a guest searches venues or coordinators in-app, surface 'Plan your event with Setnayan' prompt.

Cadence cap: maximum 1–2 marketing touches per quarter for non-engaged guests. Zero unsolicited marketing during the first 30 days post-event — that window is reserved for the album experience.

## 4.5 Founder-led storytelling

In a free-tools market dominated by global generalists, the founders' story is the differentiator. Treat Setnayan as a media company that ships a product. Weekly LinkedIn cadence; monthly Substack essay; quarterly transparency report (sign-ups, revenue, NPS, top mistake). Founders' faces on the box. This is how brand premium is earned in 12 months.

# 5. Pricing Rollout

Pricing is itself a GTM tool. The roll-out strategy below uses scarcity, founding-member status, and date-aware pricing to accelerate paid conversion in months 1–6.

## 5.1 Founding member offer (months 1–3)

- First 500 paying couples get a ₱500 discount on Premium and Pro Event tiers.

- Founding members get lifetime app access at no additional cost (a ₱3,999 add-on bundled in).

- Founding members are featured in case studies (with explicit consent) — fuels earned media.

## 5.2 Tiered launch sequence

- Month 1: Soft launch to waitlist only. Free + Essentials available; Premium gated for the concierge pilot couples.

- Month 2: Public launch of all four tiers. Founding member pricing live.

- Month 4: Standard pricing live; founding member offer ends. Add-on catalog expanded with Premium Filter Packs and Photo Books.

- Month 7: Photo Team service launches at scale. Concierge Planning Assistant available.

- Month 10: Lifetime Access promotion (anchor month for high-margin add-on conversion).

- Month 12: V1.5 features ship; multi-religion templates, on-site print service announced.

## 5.3 Add-on attach rate plan

Spec target: 60%+ add-on attach rate among paid couples. Tactics:

- Tier comparison page that surfaces the 3 most-relevant add-ons per tier.

- Post-event upsell: AI Highlight Reel and Lifetime HD Storage are highest-converting after the wedding.

- Vendor-bundle deals: Photo Team + Premium tier sold together at a small discount.

- Soft tier limits: when free or paid couple hits 80% of resolution or storage cap, in-app prompt for upgrade.

# 6. Sales Funnel & Conversion Targets

The Year 1 funnel target. Each stage has a leading indicator that triggers a tactical response if it underperforms.

| Stage | Year 1 Target | Conversion Rate | Leading Indicator |
| --- | --- | --- | --- |
| Waitlist signups | 12,000 | — | CPL ≤ ₱150 |
| Active sign-ups (account created) | 5,000 | 42% of waitlist | Email open rate ≥ 35% |
| Event created | 3,500 | 70% of sign-ups | Time-to-event-creation ≤ 15 min |
| First guest invited | 3,000 | 86% of events created | Onboarding completion rate ≥ 80% |
| Paid conversion | 1,500 | 50% of events created (30% of sign-ups) | Free-to-paid conversion ≥ 25% |
| Active completed events | 1,200 | 80% of paid | Pre-event check-in 7 days out ≥ 90% |
| NPS ≥ 50 (couples) | Yes | — | Post-event survey response ≥ 60% |
| NPS ≥ 40 (guests) | Yes | — | Post-event survey response ≥ 30% |
| Add-on attach rate | 60% | — | Highest-attach add-on tracked weekly |

# 7. Budget & Resource Allocation (Year 1)

Indicative Year 1 GTM-side budget. Excludes engineering and operational costs already covered in V1 build budget.

| Line Item | Budget (₱) | % of GTM | Notes |
| --- | --- | --- | --- |
| Paid social acquisition (Meta + TikTok) | ₱900K | 32% | Weighted to months 4–9; CPL benchmark ₱150 |
| Influencer partnerships (10–15 nano + mid) | ₱400K | 14% | Mostly comp + fee-for-content |
| Earned media + PR retainer | ₱300K | 11% | PR agency 6-month engagement |
| Vendor partnership development | ₱150K | 5% | Travel, partnership materials, events |
| Content production (video, photo, design) | ₱350K | 12% | Weekly content series + customer stories |
| Founding-member discounts (500 × ₱500) | ₱250K | 9% | Direct marketing offset |
| Customer support tooling (Intercom etc.) | ₱120K | 4% | Year 1 license |
| Brand identity + marketing assets | ₱200K | 7% | Brand refresh, packaging, swag for partners |
| Concierge pilot weddings (10) | ₱100K | 4% | Direct cost of running manual pilots |
| Contingency / opportunistic spend | ₱180K | 6% | Reserved for unexpected wins or fixes |
| Total GTM Year 1 | ₱2.95M | 100% | Indicative; reforecast quarterly |

# 8. KPI Dashboard

Weekly, monthly, and quarterly KPIs the team reviews. Each KPI has an owner and a target. Misses trigger documented escalations.

| KPI | Cadence | Year 1 Target | Owner |
| --- | --- | --- | --- |
| Waitlist signups (cumulative) | Weekly | 12,000 | Marketing |
| CPL — paid social | Weekly | ≤ ₱150 | Growth |
| Active sign-ups | Weekly | 5,000 | Product |
| Free-to-paid conversion % | Monthly | ≥ 25% | Product |
| Paid conversions | Monthly | 1,500 by year-end | Founder |
| Add-on attach rate (paid couples) | Monthly | ≥ 60% | Product |
| NPS — couples | Per-event | ≥ 50 | Customer Success |
| NPS — guests | Per-event | ≥ 40 | Customer Success |
| Crash-free sessions (iOS/Android) | Daily | ≥ 99.5% | Engineering |
| Photo upload success rate | Daily | ≥ 98% | Engineering |
| Per-event cost-to-deliver (free tier) | Monthly | ≤ ₱300 | Founder |
| Vendor partners onboarded (cumulative) | Monthly | 100 by year-end | Marketing |
| Earned media placements | Monthly | 30+ Year 1 | Marketing |
| Guest-to-couple conversion (12-mo trailing) | Quarterly (from month 7) | ≥ 1% | Founder |

# 9. Risks To The GTM Plan

Five risks that could break the plan, with mitigations.

| Risk | Impact | Mitigation |
| --- | --- | --- |
| CPL stays >₱150 in months 1–3 | Year 1 paid conversion target slips | Pivot to higher-quality, lower-volume channels (vendor referrals, earned media); reduce paid social spend |
| Vendor partners don't refer enough couples | 30–40% zero-CAC channel underperforms | Add Photo Team and Coordinator Partnership programs; introduce vendor referral payment per converted booking |
| Free tier costs scale faster than paid revenue | Unit economics break | Tighten free tier scope; cap photos per event; introduce soft prompts at 50%, 80%, 95% of usage |
| A competitor (Joy, WedPlanner) launches similar QR feature | Differentiation erodes | Lock distribution faster; push founding member program harder; pivot earned media to depth-of-experience story |
| Earned media placements come slower than 30 by year-end | Brand recognition gap remains | Hire fractional PR partner earlier; offer exclusive data/research to lifestyle press; pitch founder narrative more aggressively |

# 10. Conclusion

Year 1's job is not to dominate the Philippine wedding market. It is to do four specific things: (1) sign 1,500 paying couples, (2) prove the integrated experience delivers the NPS that drives organic word-of-mouth, (3) lock in the vendor partnerships that supply zero-CAC distribution, and (4) seed the guest CRM that compounds in Years 2 and 3.

Every line in this plan is in service of one of those four. If a marketing tactic doesn't ladder back, it gets cut. If a partnership doesn't drive paid conversions or guest acquisition, it gets renegotiated. The discipline is to do fewer things harder — and to know exactly what each thing produces.

“Year 1 is about earning trust. Year 2 is about compounding it.”